Statement of Work

LIGHT VEHICLE RADIOGRAPHY SYSTEM Begin-Terminal Site

SECTION 1

Introduction to the SOW

CONTENTS

1.1	Introduction	3

1.2	Location	3

1.3	Definitions	3

1.4	Work Contents Highlights	4

1.5	Document Description	4

1.6	Schedule	5

1.7	Mandatory Requirements	9

1.8	Acronyms and Abbreviations	12

SOW for LIGHT VEHICLE RADIOGRAPHY SYSTEM Begin-Terminal Site

Introduction

This SOW (Statement of Work) constitute a Turn Key Project (TKP) the planning, construction, installation and maintenance of a complete facility designated for security and customs checks of light vehicles by means of radiography inspection.

Location

The facility shall be erected as part of the Begin-Terminal.

Definitions

Client/Customer - The Client/Customer is Israel Tax Authority (I.T.A.)

Contractor – the company with whom the contract, for executing the project of vehicles inspection site, is signed as result of this tender.

TP – Tender Publication

Site operator - The facility shall be operated by the I.T.A

Israel Police – Security issues of site operation shall be under the guidance of the Israeli Police.

IAA – Israel Airports Authority- Landlord of the Begin Terminal

CR/CTA – Client's Representative / Client’s Technical Advisor. Performance of the work as required by this SOW shall be supervised by the CR/ LAVID Engineering LTD.

Work Contents Highlights

The Client hereby orders, and the awarded company is obligated to supply the site, the design, the systems and the services as specified in this document and the Annexed documents.

The Contractor, following contract sign, will perform the required works in order to provide the Client with a fully operational site, as defined here and after and enclosed Annex.

The work contents highlights of this TKP include supply and implementation of:

Detailed site and systems design, Design review meetings

Civil works and building construction, including all infrastructures which include removal of the old structures and facilities and building temporary structures.

Design and build an explosion-proof wall in accordance with the instructions of the Israel Airports Authority according to documents No' 140719-1 & 140719-2

(Option – by client approval only)

Verification acceptance test of the Radiography system

Factory Acceptance Tests for main systems (at the Factory site).

Systems manufacturing

Equipment transportation, release from ports, etc.

Installation of the Radiography system, defined traffic control systems, safety and security systems and all auxiliary subsystems

Acceptance Tests

Training sessions and Pilot

Final Acceptance Test

Service and Maintenance for 10 years – defined in the annex.

Document Description

This document defines the required scope of the work as follows:

Section 1 - Introduction

Section 2 - General provisions -

Description of project outlines and project procedures

Section 3 - Site Operational procedures

Description of the processes taking place in the site's designated environment, and how the Radiography system shall be integrated into them

Section 4 - Required main assemblies

Description of the site and its main components

Section 5 – The Radiography System:

Description of system's minimal requirements, testing procedures, and performance evaluation methods;

Section 6 – Technical Specifications

Systems design principles, guidelines and specifications.

1.5.7 Section 7 – The Generic Site and its components

Schedule

The schedule for implementation of the work as required by this SOW (table 1) shall be not longer than 30 calendar months After Effective Date of Contract (AEDC) in which no later than 18 calendar months after receiving both starting building permits (Tent and Radiography building including population, fully operational Radiography system and instructional courses). This time period shall cover all the stages of detailed planning needed, required export and import licenses, certifications, construction permit, complete execution of all construction works and radiographic system facilities including auxiliary systems as detailed in this SOW, and success in meeting the requirements of the Final Acceptance Test.

The works will end no later than the time periods in the schedule given in table 1:

| STEP | Step description | Date of completion from the W.O |
| --- | --- | --- |
| 00 | Work Order | 0 months |
| 01 | Submission of the architectural plans (permanent + temporary sites) | 0.5 month (two weeks from signing) |
| 02 | Submission of full list of plans | 1 month |
| 03 | Submission of the final plan to the client for permit | 3 months |
| 04 | Issuing a permit request- Contractor Responsibility Only! (Delay in issuing the permit for any reason shall not constitute grounds for such or other requests on behalf of the Contractor) | 4 months |
| 05 | Submission of detailed plans for authorization | 5 months |
| 06 | Receiving building permit | 10 months |
| 07 | Erecting the temporary site | 13 months |
| 08 | Demolishing the old Customs site | 14 months |
| 09 | Construction of the new Customs site | 26 months |
| 10 | F.A.T | 18 months |
| 11 | Manufacturing the Radiography system and its arrival to the site | 10-22 months |
| 12 | Installation | 22-23 months |
| 13 | Receiving housing permit and operation | 26 months |
| 14 | Testing | 26 months |
| 15 | Training courses | 27 months |
| 16 | Pilot | 27-29 months |
| 17 | Removal of temporary site | 28 months |
| 18 | Final acceptance test and full operation | 30 months |

Table 1: Time table for the Begin-Terminal SOW

The contractor must comply with the schedule as mentioned in the time table of table 1.

Conceptual flow chart to temporary site and permanent site

| Conceptual flow chart for project |  |  | Update date: |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| no | Process name | Status |  | Start date | End date | Remarks |
| 1. | Building permit |  |  |  |  |  |
| 1.1 | Information file |  |  |  |  |  |
| 1.2 | Start of permit (basic plans) |  |  |  |  |  |
| 1.3 | Design (detailed plans) |  |  |  |  |  |
| 1.4 | Receiving of building permit |  |  |  |  |  |
| 2. | Business license (if needed) |  |  |  |  |  |
| 2.1 | In respect to building permit, construction finish and “Tofes 4”. |  |  |  |  |  |
| 3. | Engineering |  |  |  |  |  |
| 3.1 | Primary survey-for system requirements (SRR) |  |  |  |  |  |
| 3.1.1 | Client’s requests survey |  |  |  |  |  |
| 3.1.2 | Building a program |  |  |  |  |  |
| 3.1.3 | Client’s program approval |  |  |  |  |  |
| 3.2 | Preliminary Design Review (PDR) (The plans will be submitted to a building permit) |  |  |  |  |  |
| 3.2.1 | Architectural |  |  |  |  |  |
| 3.2.2 | Construction |  |  |  |  |  |
| 3.2.3 | Power/electricity /ELF/ Communication systems |  |  |  |  |  |
| 3.2.4 | Water, Plumbing and fire detection and extinguishing systems |  |  |  |  |  |
| 3.2.5 | A/C and fume release ducts |  |  |  |  |  |
| 3.2.6 | Safety and Accessibility |  |  |  |  |  |
| 3.2.7 | Compressed air |  |  |  |  |  |
| 3.2.8 | Acoustics |  |  |  |  |  |
| 3.2.9 | Security and Control |  |  |  |  |  |
| 3.2.10 | Client Plan's approval |  |  |  |  |  |
| 3.3 | Detailed Design Review (DDR) |  |  |  |  |  |
| 3.3.1 | Detailed Plans mapping by planners (as Noted and Approved by client above in PDR) |  |  |  |  |  |
| 3.3.2 | Client Plan's approval |  |  |  |  |  |
| 4. | Critical Design Review (CDR) |  |  |  |  |  |
| 4.1 | Plans to be executed in accordance with the customer's approval (as Noted and Approved by client above in DDR) |  |  |  |  |  |
| 4.2 | Client Plan's approval |  |  |  |  |  |
| 5. | Completions of Engineering |  |  |  |  |  |
| 5.1 | Updates during executions |  |  |  |  |  |
| 6. | Execution of works |  |  |  |  |  |
| 6.1 | Start work order |  |  |  |  |  |
| 6.2 | Start of work with detailed definition for the initial work content |  |  |  |  |  |
| 6.3 | Quality control by the contractor and submission of reports for customer approval |  |  |  |  |  |
|  | Management and oversight while constant updating the client |  |  |  |  |  |
| 6.4 | Primary delivery of work (infrastructure input in accordance with the governmental housing unit) |  |  |  |  |  |
| 6.5 | Amendment of errors and defects |  |  |  |  |  |
| 6.6 | Final delivery |  |  |  |  |  |
| 6.7 | Delivery of site’s file by the contractor |  |  |  |  |  |

Mandatory Requirements

Bidder / Contractor Qualifications (defined in the contract)

Have proven experience, either directly or with the aid of Sub-contractors, in delivery of a Turn Key Project (TKP) for a complete inspection site, including planning, construction, installation and maintenance of complete radiographic facility for vehicle checks utilizing high-energy X-Ray inspection.

In the event that a consortium of companies possesses the required accumulated experience, it will be clearly stated who is the main contractor. A copy of the written agreement between the members of the consortium must also be submitted with the proposal.

Have proven experience of at least five (5) years (2012-2019) in manufacture, supply and maintenance of an operational working system of the following scanning configuration (Conveyor): the emission and detector subsystems are stationary along a moving object, utilizing X-Ray emission subsystem with energy higher than 1 MeV.

Have the ability to provide comprehensive Service and Maintenance for the radiography system.

Radiography System Minimal Requirements

The radiography system and all auxiliary systems will comply with Israeli law and regulations.

The radiographic system will be able to scan and image an object, with dimension equal to one (1) vehicle,  of total length of up to 5 [m], and to display the image of on the screen without any distortion or corner cut-off.

      - The System Minimum Performance, expressed in parameters defined in chapter 5 of this SOW, shall be:

      - Ultimate Penetration

        - The Ultimate Penetration will be at least 160 [mm] Stainless Steel, at least at three different locations (out of the 9 defined positions) at scan velocity of 12 [m/min].

        - The Ultimate Penetration will be at least 130 [mm] Stainless Steel at each of the 9 defined positions at scan velocity of 12 [m/min].

      - Resolution

        - Wire resolution, when measured at the middle of the object at height   corresponding to the center of the beam (best position) will be, at least:

        - 2.5% for 50 [mm] clutter (1.25 [mm] Stainless Steel wire behind 50 [mm] of Stainless Steel)

        - 2.5% for 100 [mm] clutter (2.5 [mm] Stainless Steel wire behind 100 [mm] of Stainless Steel)

Contrast

        - The systems contrast shall be no more than 3% behind 50 [mm] Stainless Steel. The Radiography system manufacturer will declare the contrast quality of the system by using Hole-Type Image Quality Indicators (IQI) indicators in accordance with the guidelines of the ASTM standard E 1025 latest edition: “Standard Practice for Planning, Manufacture, and Material Grouping Classification of Hole-Type Image Quality Indicators (IQI) Used for Radiology.

Material Discrimination

Material Discrimination mode, differentiating between organic and inorganic material, shall be an integrate part of the system. It will be able to distinguish materials such as organic material and inorganic material and mark them by different colors.

The material discrimination application, designated to improve image analysis, will not significantly deteriorate the operational capabilities (for example: inspection times, penetration and resolution) of the Radiography system

Throughput

The Radiography system will be able to inspect at least 24 [vehicles/hour].

Acronyms and Abbreviations

| AEDC | After Effective Date of Contract |
| --- | --- |
| CC/CCR | Container Code / Container Code Recognition |
| CCTV | Closed Circuit Television |
| CDR | Critical Design Review |
| CQCS | Contractor’s Quality Control System |
| CR/CTA | Client's Representative /Client's Technical Advisor |
| DR | Design Review |
| DDR | Detailed Design Review |
| EC | Evaluating Committee |
| FCS | Facility Control System |
| FAT | Factory Acceptance Test |
| GOI | Government of Israel |
| IAA | Israel Airports Authority |
| IAW | Image Analyst Workstation |
| IDS ITA | Intrusion Detection System Israel Tax Authority |
| LP/LPR/ALPR | License Plate Number/Automatic License Plate Recognition |
| OCR | Optical Character Recognition |
| OM | Operation & Maintenance |
| PA | Public Address |
| PDR | Preliminary Design Review |
| QC | Quality Control |
| RCW | Re-Check Workstation |
| RCS | Radiography Control System |
| SAT | Site Acceptance Test |
| SDMS | Shipment Directing and Monitoring System |
| SO | System Operator |
| SOW | Statement Of Work |
| TCS | Traffic Control System |
| TKP | Turn Key Project |
| UPS | Uninterrupted Power Supply |
| WS | Workstation |

Important notices:

The plans and drawing presented in this document (the entire Bid and all its sections) is for conceptual purposes only. The contractor must provide full plans, drawings, 3D drawings and imaging, documentation, licenses and permits of any kind that are needed for this TKP and which are mandatory.

Contractor's delay in submitting documents for Client's approval beyond schedule shall not constitute a cause for a claim by the Contractor to extend the time allocated for the project implementation.

In addition, if the drawings are submitted in time but are rejected by the Client, returned to the Contractor and re-submitted for approval, no claim to extend the planning and implementation period of the project will be accepted and this delay will not constitute a cause for canceling delay liquidated damages.

List of Conceptual Drawings:

| Files | Description |
| --- | --- |
| The Site: |  |
| 143-05-001.pdf | Begin-Terminal site plan |
| 143-05-002.pdf | Begin-Terminal site, temporary and permanent sites Assignment |
| 143-05-004.pdf | Begin-Terminal site, tent’s floor plan |
| 143-05-005.pdf | Begin-Terminal site, tent assignment plan |
| The Building: |  |
| 143-05-003-SH#1.pdf | Begin-Terminal site, Permanent building, pit and ground floor |
| 143-05-003-SH#2.pdf | Begin-Terminal site, Permanent building, first floor and roof top |
| 143-05-003-SH#3.pdf | Begin-Terminal site, Permanent building, building sections |
| 143-05-003-SH#4.pdf | The Generic Radiography building facility, Generic site |